## Bob
Date | Hours | Task
2020-10-20 | 3 | Setup GitHub, Registering CMT, writing project proposal, updating README
2020-11-07 | 0.75 | Spent time becoming familiar with EducationalWeb utility
2020-11-11 | 1.75 | Copy source code into GitHub, begin reviewing code, start setting up local environment
2020-11-13 | 0.25 | Continued setting up local environment
2020-11-14 | 0.75 | Trying to debug local environment setup issues and corrupted ZIP file
2020-11-17 | 0.5 | Struggling with local environment, reaching out to other teams, TAs, etc.
2020-11-18 | 0.25 | Investigating possible solution to corrupted ZIP file and instlling GULP.js
2020-11-23 | 0.5 | Working with Huang on EducationalWeb installation in Windows - he is also having problems
2020-11-24 | 0.5 | Working with Cullen on EducationalWeb installation; Cullen has success on a Mac
2020-11-27 | 4 | FINALLY got EducationalWeb installed in local environment, began working on multiple download
2020-11-29 | 0.5 | Creating Project Progress Report, updating README
2020-12-01 | 1.5 | Reading code, finding where to update download logic, began duplicating for download-series logic
2020-12-02 | 3.75 | 6:00 meeting with Cullen to work on download series logic, button arrangement, how to call functions
2020-12-03 | 1.25 | Worked with Huang, found a file name and directory name length limitation in Windows that may be what's causing us problems
2020-12-05 | 2 | Worked on JSZip.js and FileSaver.js for proof of concept on zipping multiple files. Having difficulty with path lengths.
2020-12-07 | 0.25 | Worked with Cullen, confirmed my proof of concept is working on Mac machine
2020-12-08 | 2.75 | Meeting with team, worked through zipping multiple files, started looking for ways to zip an entire folder of files at once
2020-12-09 | 3 | Researching Node.js, Jquery, PHP, Ajax, Kintone, etc. looking for ways to get a list of all files within a server directory
2020-12-10 | 2.75 | Continued struggling with how to zip entire folder at once. Started test case with hard-coded file lists, which was less-than-optimal
2020-12-11 | 2.25 | GOT IT. By using file name convention, looping, and ignoring 404 errors, I can zip an entire directory without knowing its contents
2020-12-12 | 1 | Met with team, showed solution, worked with Cullen on how to set it up to work with his calling method, started documentation
2020-12-13 | ? | Finishing documentation, video, arranging demo with reviewers
| 33.25 | Total time spent on project

## Cullen
Date | Hours | Task
| 0 | Total time spent on project

## Huang
Date | Hours | Task
| 0 | Total time spent on project